## FMEA
Failure Mode # | Subsystem | Failure Mode | Failure Effects | Possible Cause | Failure Effects Severity | Occurrence Likelihood | Risk Priority Number (RPN) (=severity * occurrence) | Risk Criticality (Corrective Action Priority) |  | Corrective Action | Failure Effects Severity | Occurrence Likelihood | Risk Priority Number (RPN) | Criticality (Corrective Action Priority) | Corrective Action Effort | Corrective Action | Failure Effects Severity | Occurrence Likelihood | Risk Priority Number (RPN) | Criticality (Corrective Action Priority) | Corrective Action Effort | Troubleshooting (optional)
F.1 | IR Sensor Encoder | Reported number of rotations from the IR sensor is too few | Demand incorrectly larger than necessary, Energy usage is larger than necessary, Bicycle goes far faster than desired | sensor detector or emitter is partially blocked or damaged, | 4 | 5 | 20 | HIGH |  | Add a shielding cone to the detector. Add a sweep to the emitter just before it passes the detector to help clear the emitter off. Increase the intensity of the emitter. Research more robust parts. Put in a redundant encoder and adjust sensor filter system to account for this redundancy. Ensure manual override system is functioning properly. | 4 | 2 | 8 | MEDIUM | 15 hrs. (See Timeline's IR Sensor Risk Plan B) | Use COTS Encoder. Put in a redundant encoder and adjust sensor filter system to account for this redundancy. Ensure manual override system is functioning properly. | 4 | 1 | 4 | MEDIUM LOW | 10 hrs. (See Timeline's IR Sensor Risk Plan E) | Check encoders to make sure they are securely fastened and properly aligned. Check encoders for debris and clean if need be. Check encoders to make sure they're still working. Replace encoders if need be.
|  |  |  | sensor detector or emitter is damaged | 4 | 2 | 8 | MEDIUM |  | Research more robust parts. Put in a redundant encoder and adjust sensor filter system to account for this redundancy. Ensure manual override system is functioning properly. | 4 | 1 | 4 | MEDIUM LOW | 12 hrs. (See Timeline's IR Sensor Risk Plan B)
|  |  |  | sensor detector or emitter has become loose or is no longer oriented properly | 4 | 4 | 16 | MEDIUM HIGH |  | Increase the robustness of the mechanical housing. Included checking its secureness as part of the recommended start up safety check. Put in a redundant encoder and adjust sensor filter system to account for this redundancy | 4 | 1 | 4 | MEDIUM LOW | 12 hrs. (See Timeline's IR Sensor Risk Plan B and Plan C)
F.2 |  | Reported number of rotations from the IR sensor is too many | Demand incorrectly as smaller than necessary, Energy storage is conserved or even increased more than it should be, Bicycle goes far slower than desired | sensor detector or emitter is partially damaged | 2 | 1 | 2 | LOW | [13 empty] | Check encoders to make sure they are securely fastened and properly aligned. Check encoders for debris and clean if need be. Check encoders to make sure they're still working. Replace encoders if need be.
F.3 |  | No signal provided | Sensor Filter System reports error. Demand Algorithm Reports Error. Controller switches to energy storage only, no usage. GUI reports error. Bicycle functions inefficiently until user disengages PMB engine | broken detector or emitter | 2 | 2 | 4 | MEDIUM LOW |  | Research more robust parts. Put in a redundant encoder and adjust sensor filter system to account for this redundancy. | 2 | 1 | 2 | LOW | 12 hrs. (See Timeline's IR Sensor Risk Plan B) | [6 empty] | Check encoders to make sure they are securely fastened and properly aligned. Check wiring for frays and proper connections. Replace encoders or connections if need be.
|  |  |  | power cables disconnected | 2 | 4 | 8 | MEDIUM |  | Increase the robustness of the mechanical housing to take stress of cable connections | 2 | 1 | 2 | LOW | 3 Hrs. (See Timeline's IR Sensor Risk Plan D)
|  |  |  | signal cables disconnected | 2 | 5 | 10 | MEDIUM |  | Increase the robustness of the mechanical housing to take stress of cable connections | 2 | 1 | 2 | LOW | 3 Hrs. (See Timeline's IR Sensor Risk Plan D)
|  |  |  | Likelihood | Current # of Risks Shown Stoplight Graph |  |  |  |  | Likelihood | Current # of Risks Shown Stoplight Graph |  |  |  |  | Likelihood | Current # of Risks Shown Stoplight Graph
|  |  |  | 5 | 0 | 1 | 0 | 1 |  | 5 | 0 | 0 | 0 | 0 |  | 5 | 0 | 0 | 0 | 0
|  |  |  | 4 | 0 | 1 | 0 | 1 |  | 4 | 0 | 0 | 0 | 0 |  | 4 | 0 | 0 | 0 | 0
|  |  |  | 3 | 0 | 0 | 0 | 0 |  | 3 | 0 | 0 | 0 | 0 |  | 3 | 0 | 0 | 0 | 0
|  |  |  | 2 | 0 | 1 | 0 | 1 |  | 2 | 0 | 0 | 0 | 1 |  | 2 | 0 | 0 | 0 | 0
|  |  |  | 1 | 0 | 1 | 0 | 0 |  | 1 | 0 | 4 | 0 | 2 |  | 1 | 0 | 4 | 0 | 3
[5 empty] | 1 | 2 | 3 | 4 | Severity |  | 1 | 2 | 3 | 4 | Severity |  | 1 | 2 | 3 | 4 | Severity

## RPN Definitions
Severity
4 | Cost is more than 20% of the total budget, Requires more than 2 weeks to address, Performance is adversely affected by greater than 20%, Causes potential harm to a person
3 | Cost is 10%-20% of the total budget, Requires 1-2 weeks to address, Performance is adversely affected by 10-20%, no harm to a person
2 | Cost is 5%-10% of the total budget, Requires 1-6 days to address, Performance is adversely affected by 5-10%, no harm to a person
1 | Cost is less than 5% of the total budget, Requires less than 1 day to address, Performance is adversely affected by less than 5%, no harm to a person
Likelihood (in prototype development: all these levels would be too often for a final product)
5 | Occurs greater than once a week, Occurs in greater than 10% of the operations
4 | Occurs greater than once a week, Occurs in 5-10% of the operations
3 | Occurs no more than once a week
2 | Occurs between to once every 2 weeks to once every 3 months
1 | Occurs less than once every 3 months
Risk Priority Number (RPN) Definition Table | [5 empty] | Risk Criticality Ranges
Likelihood
5 | 5 | 10 | 15 | 20 |  | 15-20 | High Risk
4 | 4 | 8 | 12 | 16 |  | 9-14 | Medium High Risk
3 | 3 | 6 | 9 | 12 |  | 5-8 | Medium Risk
2 | 2 | 4 | 6 | 8 |  | 3-4 | Medium Low Risk
1 | 1 | 2 | 3 | 4 |  | 1-2 | Low Risk
| 1 | 2 | 3 | 4 | Severity