## Slide 1
Solar Panel Analysis for Community Hall
List of All Panel Options
Investigated on Power
Payback Periods
Calculate Solar Power Generation
Battery Storage Options
Determine Top 3 Panel Choices
Power Consumption / Generation Chart
Building Renderings with Solar Panels Installed for min 1 Top Panel Choice
Documentation on Related Building Code Compliance
Installation Cost Estimates
Anticipated Maintenance Schedule & Costs
Choices
Cost Estimates
Parts Costs
Labor Costs
This is a first pass at the deliverables that need to be completed in order to satisfy the “analysis”. Some are broken down further. Some aren’t even connected in yet. It is clear already though that some structure is beginning to take shape but that most, if not all, of these will have to be explored further.
Notice that boxes aren’t placed precisely. They’re most likely going to be added to / moved around later anyways.
Analysis

## Slide 2
Solar Panel Analysis for Community Hall
List of All Panel Options
Investigated on Power
Payback Periods
Calculate Solar Power Generation
Battery Storage Options
Determine Top 3 Panel Choices
Power Consumption / Generation Chart
Building Renderings with Solar Panels Installed for min 1 Top Panel Choice
Documentation on Related Building Code Compliance
Installation Cost Estimates
Anticipated Maintenance Schedule & Costs
Choices
Cost Estimates
Parts Costs
Labor Costs
Just a little bit of organization. We noticed that we’re going to need as part of the list of panels, cost estimates for most, if not all, all of panel types we investigate (unless maybe a panel type is really bad in some other way and its cost isn’t worth looking into.) So we moved the cost estimates and moved under the list.
We may find we want to move it again later and that’s certainly okay. This is still a very rough, just get the ideas down on paper, level of work.
Analysis

## Slide 3
List of All Panel Options
Investigated on Power
Payback Periods
Calculate Solar Power Generation
Determine Top 3 Panel Choices
Power Consumption / Generation Chart
Installation Cost Estimates
Anticipated Maintenance Schedule & Costs
Choices
Cost Estimates
Parts Costs
Labor Costs
Determining the Top 3 Panel Choices seems like it has a lot of important tasks going into it, so let’s just explore this branch for a bit
Analysis.3Panels

## Slide 4
Notice the branch is
labeled for easy referencing later on
Analysis.3Panels
You can give it any name you want. It’s just best to make sure it has a clear and unique meaning.
List of All Panel Options
Investigated on Power
Payback Periods
Calculate Solar Power Generation
Determine Top 3 Panel Choices
Power Consumption / Generation Chart
Installation Cost Estimates
Anticipated Maintenance Schedule & Costs
Choices
Cost Estimates
Parts Costs
Labor Costs

## Slide 5
List of All Panel Options
Investigated on Power
Payback Periods
Calculate Solar Power Generation
Determine Top 3 Panel Choices
Power Consumption / Generation Chart
Installation Cost Estimates
Anticipated Maintenance Schedule & Costs
Choices
Cost Estimates
Parts Costs
Labor Costs
Frequency of Maintenance
Cost of Maintenance
Time to Complete Maintenance
Expertise needed to do Maintenance
Estimated Complexity
Time to Complete Project
Expertise needed to Complete Project
Estimated Complexity
Must be within time constraints
Labor Safety Issues
Analysis.3Panels
Adding in some performance criteria for the some of the cost and maintenance parts.
…we’ll color performance criteria light yellow and…
Normally, you might not color anything until the end because it’s easier to keep track of what’s what if you’ve written it. For this example…
…we’ll color data
light green….
…and leave the rest white for now

## Slide 6
List of All Panel Options
Investigated on Power
Payback Periods
Calculate Solar Power Generation
Determine Top 3 Panel Choices
Power Consumption / Generation Chart
Installation Cost Estimates
Anticipated Maintenance Schedule & Costs
Choices
Cost Estimates
Parts Costs
Labor Costs
Frequency of Maintenance
Cost of Maintenance
Time to Complete Maintenance
Expertise needed to do Maintenance
Estimated Complexity
Time to Complete Project
Expertise needed to Complete Project
Estimated Complexity
Must be within time constraints
Labor Safety Issues
The newly added performance criteria for the some of the cost and maintenance parts, makes it clear that there’s going to be a lot more to do here…
Analysis.3Panels

## Slide 7
Installation Cost Estimates
Anticipated Maintenance Schedule & Costs
Choices
Cost Estimates
Parts Costs
Labor Costs
Frequency of Maintenance
Cost of Maintenance
Time to Complete Maintenance
Expertise needed to do Maintenance
Estimated Complexity
Time to Complete Project
Expertise needed to Complete Project
Estimated Complexity
Must be within time constraints
Labor Safety Issues
…so let’s explore just this cost branch
Analysis.3Panels.CostEst

## Slide 8
Installation Cost Estimates
Anticipated Maintenance Schedule & Costs
Choices
Cost Estimates
Parts Costs
Labor Costs
Frequency of Maintenance
Cost of Maintenance
Time to Complete Maintenance
Expertise needed to do Maintenance
Estimated Complexity
Time to Complete Project
Expertise needed to Complete Project
Estimated Complexity
Must be within time constraints
Labor Safety Issues
The following slides share some thoughts on how this branch is grown further…
Analysis.3Panels.CostEst
Notice how the naming grows to show where this branch came from

## Slide 9
Installation Cost Estimates
Anticipated Maintenance Schedule & Costs
Choices
Cost Estimates
Parts Costs
Labor Costs
Frequency of Maintenance
Cost of Maintenance
Time to Complete Maintenance
Expertise needed to do Maintenance
Estimated Complexity
Time to Complete Project
Expertise needed to Complete Project
Estimated Complexity
Must be within time constraints
Labor Safety Issues
Looking to add the Government Incentives, this new branch quickly runs off the slide
Analysis.3Panels.CostEst
Government Incentive Options
Qualification Requirements
Application Procedure
Which Stakeholder Contact would have to handle this?
Discuss w/ Stakeholder Contact who would have to handle this
That’s not uncommon while you’re in the middle of working on this...

## Slide 10
Installation Cost Estimates
Anticipated Maintenance Schedule & Costs
Choices
Cost Estimates
Parts Costs
Labor Costs
Frequency of Maintenance
Cost of Maintenance
Time to Complete Maintenance
Expertise needed to do Maintenance
Estimated Complexity
Time to Complete Project
Expertise needed to Complete Project
Estimated Complexity
Must be within time constraints
Labor Safety Issues
Analysis.3Panels.CostEst
Analysis.3Panels.
CostEst.GovtIncent
…so just cut it off and indicate where you can find it using the branch labels

## Slide 11
Government Incentive Options
Qualification Requirements
Application Procedure
Which Stakeholder Contact would have to handle this?
Discuss w/ Stakeholder Contact who would have to handle this
Research Government Websites
Contact Government Representatives
Determine Time Periods
Are there other criteria to use to know which ones to recommend?
Analysis.3Panels.CostEst.GovtIncent
Whether to repeat this node for each higher-up-the-branch-node, or connect this node to both higher-up-the-branch-nodes, as is done here, depends on the situation. Most of the time you’ll want to repeat the node, but here we believe that both higher-up-the-branch-nodes’ needs can be easily met at the same time while addressing this node so its okay we didn’t repeat this node.
Said another way, the person who does the “Research Government Websites” task can meet both the “Determine Time Periods” and “Qualification Needs” at the same time more easily than if you asked two people to address “Determine Time Periods” and “Qualification Needs” separately.
Now back to the main Cost Estimates branch…

## Slide 12
Installation Cost Estimates
Anticipated Maintenance Schedule & Costs
Choices
Cost Estimates
Parts Costs
Labor Costs
Shipping Costs
Parts Availability
Frequency of Maintenance
Cost of Maintenance
Time to Complete Maintenance
Expertise needed to do Maintenance
Estimated Complexity
Time to Complete Project
Expertise needed to Complete Project
Estimated Complexity
Must be within time constraints
Labor Safety Issues
How do you measure complexity?
Reliability of Panels
Research Data Sheets for Information
Contact Panel Vendors for Information,
Maybe references of where panels are already used
Analysis.3Panels.CostEst
Noticed there was more data that would be needed, so let’s add that in
Most of the criteria above sound reasonable but I’m not sure what the stakeholder means by complexity…
What goes into reliability? Let’s add tasks to check these sources as a start. May need to add more tasks later depending how this goes…
We’re going to have to find out
Growing the other branches…
Analysis.3Panels.
CostEst.GovtIncent

## Slide 13
Installation Cost Estimates
Anticipated Maintenance Schedule & Costs
Choices
Cost Estimates
Parts Costs
Labor Costs
Shipping Costs
Parts Availability
Frequency of Maintenance
Cost of Maintenance
Time to Complete Maintenance
Expertise needed to do Maintenance
Estimated Complexity
Time to Complete Project
Expertise needed to Complete Project
Estimated Complexity
Must be within time constraints
Labor Safety Issues
How do you measure complexity?
Reliability of Panels
Research Data Sheets for Information
Contact Panel Vendors for Information,
Maybe references of where panels are already used
Contact Panel Vendors for Information
Contact Contractors for Estimates
Contact Contractor for Needed Information
What other info do they need?
Select possible “Baseline” Panel just for establishing criteria baselines of comparison
Analysis.3Panels.CostEst
Building Size
Roof Size
Roof Weight Constraints
Roof Attachment Constraints
Setting a baseline of comparison early on. Any standard panel should serve us fine… perhaps the vendor can suggest one
We’ll work
off of
estimates for now. We
We may have to redo these steps for our final top 3 panels, and it may even change which panels are our top 3, which is fine.
just need a ballpark figure and this will help us build intuition.
Growing the other branches further…
Analysis.3Panels.
CostEst.GovtIncent

## Slide 14
Installation Cost Estimates
Anticipated Maintenance Schedule & Costs
Choices
Cost Estimates
Parts Costs
Labor Costs
Shipping Costs
Parts Availability
Frequency of Maintenance
Cost of Maintenance
Time to Complete Maintenance
Expertise needed to do Maintenance
Estimated Complexity
Time to Complete Project
Expertise needed to Complete Project
Estimated Complexity
Must be within time constraints
Labor Safety Issues
How do you measure complexity?
Reliability of Panels
Research Data Sheets for Information
Contact Panel Vendors for Information,
Maybe references of where panels are already used
Contact Panel Vendors for Information
Contact Contractors for Estimates
Contact Contractor for Needed Information
What other info do they need?
Select possible “Baseline” Panel just for establishing criteria baselines of comparison
Analysis.3Panels.CostEst
Branches commonly end with…
…questions or requests for additional resources to allow you to proceed
… atomic tasks that we know how to complete
…sets of data that are already known or need to be obtained
Building Size
Roof Size
Roof Weight Constraints
Roof Attachment Constraints
Analysis.3Panels.
CostEst.GovtIncent

## Slide 15
Installation Cost Estimates
Anticipated Maintenance Schedule & Costs
Choices
Cost Estimates
Parts Costs
Labor Costs
Shipping Costs
Parts Availability
Frequency of Maintenance
Cost of Maintenance
Time to Complete Maintenance
Expertise needed to do Maintenance
Estimated Complexity
Time to Complete Project
Expertise needed to Complete Project
Estimated Complexity
Must be within time constraints
Labor Safety Issues
How do you measure complexity?
Reliability of Panels
Research Data Sheets for Information
Contact Panel Vendors for Information,
Maybe references of where panels are already used
Contact Panel Vendors for Information
Contact Contractors for Estimates
Contact Contractor for Needed Information
What other info do they need?
Select possible “Baseline” Panel just for establishing criteria baselines of comparison
Analysis.3Panels.CostEst
Building Size
Roof Size
Roof Weight Constraints
Roof Attachment Constraints
…branches may also end with performance criteria.
(This case is not shown here.)
Analysis.3Panels.
CostEst.GovtIncent

## Slide 16
List of All Panel Options
Investigated on Power
Payback Periods
Calculate Solar Power Generation
Power Consumption / Generation Chart
Calc. Number of Panels on Building
Building Size
Analysis.3Panels.PanelList
Returning back to the Determine 3 Panels node and the exploring down another branch
Recognize that the number of panels is probably going to be dependent on what the architectural code allows, so this will need to be flushed out more…
Architectural Code Requirements

## Slide 17
List of All Panel Options
Investigated on Power
Payback Periods
Calculate Solar Power Generation
Power Consumption / Generation Chart
Adjust Calc. # of Panels on Building & Their Location to meet Code
Calc. Est. of # of Panels on Building & Their Location
Create documentation to show the panels will meet architectural code
Building Size
Roof Size
Roof Weight Constraints
Roof Attachment Constraints
Create List of Possible Panels
Does the stakeholder have any initial preferences?
Panel Sizes
Panel Attachment Constraints
Hmm, turns out we need the a plan for how the panels will be laid out on the roof to check against the code, but we don’t know for sure how they’ll be laid out until they’ve been code approved.
So let’s add in an estimate stage to use initially and then adjust from there.
Also recognize the need for more data, may need more later
Good opportunity to learn about performance criteria too
Analysis.3Panels.PanelList

## Slide 18
It’s okay to repeat nodes and info, (this data is used in more than one place)
Building Size
What does this document look like?
Who can we contact as a resource?
Where can we find out the code?
Installation Information
Analysis.3Panels.CostEst
List of All Panel Options
Investigated on Power
Payback Periods
Calculate Solar Power Generation
Power Consumption / Generation Chart
Adjust Calc. # of Panels on Building & Their Location to meet Code
Calc. Est. of # of Panels on Building & Their Location
Create documentation to show the panels will meet architectural code
Building Size
Roof Size
Roof Weight Constraints
Roof Attachment Constraints
Create List of Possible Panels
Does the stakeholder have any initial preferences?
Panel Sizes
Panel Attachment Constraints
We specified this info already, so say where it’s found
Flushing out the architectural code nodes we see there are a lot of questions, which is fine for now, and it helps make it very evident that we need to get those questions answered soon as a lot of work higher in the branch depends on it.
Analysis.3Panels.PanelList

## Slide 19
Annual Building Power Usage
  Daily averages
Analysis.3Panels.CostEst
Is there a stakeholder that can help us get this info?
Determine Incoming Solar Radiation
Electricity Costs
Determine Panel Efficiency from Data Sheets
Solar Panel Efficiency
  Factors that may effect the panels efficiency, such as including solar tracking
Are there other factors?
Building Size
What does this document look like?
Who can we contact as a resource?
Where can we find out the code?
Installation Information
Analysis.3Panels.CostEst
List of All Panel Options
Investigated on Power
Payback Periods
Calculate Solar Power Generation
Power Consumption / Generation Chart
Adjust Calc. # of Panels on Building & Their Location to meet Code
Calc. Est. of # of Panels on Building & Their Location
Create documentation to show the panels will meet architectural code
Building Size
Roof Size
Roof Weight Constraints
Roof Attachment Constraints
Create List of Possible Panels
Does the stakeholder have any initial preferences?
Panel Sizes
Panel Attachment Constraints
There’s a tendency sometimes to keep working all the way down a branch and then having to go back up to higher nodes. This is fine but here where when we flush out Calculate Solar Power Generation, we see it’s getting crowded quickly. So we’ll pull out these items onto a the next slide.
Analysis.3Panels.PanelList

## Slide 20
Determine Incoming Solar Radiation
Annual Solar Radiation
  Daily averages (local if possible, but at least for latitude)
  Local Daily Cloud Cover
  Current Local Shading
  Prediction of Local Shading for lifetime of the panels
Local Site Data
Long Term City/Campus Plans
Determine Panel Efficiency from Data Sheets
Solar Panel Efficiency
  Factors that may effect the panels efficiency, such as including solar tracking
Are there other factors?
Contact Vendors
Who can we get this info from?
Who can we get this info from?
Contact local airport for info
Look up almanac info
Analysis.3Panels.PanelList.PanelEff&SolarRad
Calculate Solar Power Generation
Analysis.3Panels.PanelList
Starting the new slide with a reference to the previous one makes it easier for the reader to recognize there’s more happening on the previous slide as well
It’s not uncommon for a number of the leaf nodes to be questions about sources of data or simply how to do things.

## Slide 21
Annual Building Power Usage
  Daily averages
Analysis.3Panels.CostEst
Is there a stakeholder that can help us get this info?
Analysis.3Panels.
PanelList.
PanelEff&SolarRad
Electricity Costs
Building Size
What does this document look like?
Who can we contact as a resource?
Where can we find out the code?
Installation Information
Analysis.3Panels.CostEst
List of All Panel Options
Investigated on Power
Payback Periods
Calculate Solar Power Generation
Power Consumption / Generation Chart
Adjust Calc. # of Panels on Building & Their Location to meet Code
Calc. Est. of # of Panels on Building & Their Location
Create documentation to show the panels will meet architectural code
Building Size
Roof Size
Roof Weight Constraints
Roof Attachment Constraints
Create List of Possible Panels
Does the stakeholder have any initial preferences?
Panel Sizes
Panel Attachment Constraints
Analysis.3Panels.PanelList
Payback Period
Energy Generation / Carbon Reduction
Building Code Compliance
Maintenance
Project Cost, Complexity & Time Required
Look Estimate
Ability to Monitor
Notice the reference to the slide we just previously made
As a good check for completeness, make sure to add in performance criteria and see if the deliverables meet all of these needs
In this case, it looks like we’ll need more deliverables still to address all of the needs & performance criteria

## Slide 22
Annual Building Power Usage
  Daily averages
Analysis.3Panels.CostEst
Is there a stakeholder that can help us get this info?
Analysis.3Panels.
PanelList.
PanelEff&SolarRad
Electricity Costs
Building Size
What does this document look like?
Who can we contact as a resource?
Where can we find out the code?
Installation Information
Analysis.3Panels.CostEst
List of All Panel Options
Investigated on Power
Payback Periods
Calculate Solar Power Generation
Power Consumption / Generation Chart
Adjust Calc. # of Panels on Building & Their Location to meet Code
Calc. Est. of # of Panels on Building & Their Location
Create documentation to show the panels will meet architectural code
Building Size
Roof Size
Roof Weight Constraints
Roof Attachment Constraints
Create List of Possible Panels
Does the stakeholder have any initial preferences?
Panel Sizes
Panel Attachment Constraints
Analysis.3Panels.PanelList
Energy Generation / Carbon Reduction
Building Code Compliance
Ability to Monitor
Create way to Estimate Look criteria value
What are the stakeholder’s way of evaluate / using the “ability to monitor”?
Meet with architectural committee rep. to determine “Look” criteria
Contact Panel Vendors
Payback Period
Split up criteria to show where and how soon we can begin to get some values (even estimates) on our performance
Look Estimate

## Slide 23
Annual Building Power Usage
  Daily averages
Analysis.3Panels.CostEst
Is there a stakeholder that can help us get this info?
Analysis.3Panels.
PanelList.
PanelEff&SolarRad
Electricity Costs
Building Size
What does this document look like?
Who can we contact as a resource?
Where can we find out the code?
Installation Information
Analysis.3Panels.CostEst
List of All Panel Options
Investigated on Power
Payback Periods
Calculate Solar Power Generation
Power Consumption / Generation Chart
Adjust Calc. # of Panels on Building & Their Location to meet Code
Calc. Est. of # of Panels on Building & Their Location
Create documentation to show the panels will meet architectural code
Building Size
Roof Size
Roof Weight Constraints
Roof Attachment Constraints
Create List of Possible Panels
Does the stakeholder have any initial preferences?
Panel Sizes
Panel Attachment Constraints
Analysis.3Panels.PanelList
Energy Generation / Carbon Reduction
Building Code Compliance
Ability to Monitor
Create way to Estimate Look criteria value
What are the stakeholder’s way of evaluate / using the “ability to monitor”?
Meet with architectural committee rep. to determine “Look” criteria
Contact Panel Vendors
Payback Period
“Ability to Monitor” is still uncertain so until we get more info., we’ll leave it here but we’ll want to get this question answered soon
Look Estimate
It’s common to have to create ways to estimate performance mid-way in your work. This kind of feedback is essential to recognize problems / opportunities early on

## Slide 24
Solar Panel Analysis for Community Hall
Analysis.
Battery Storage Options
Building Renderings with Solar Panels Installed for min 1 Top Panel Choice
Electricity Costs
“Excess” Energy
Generation
Battery Storage Capacity
Battery Charging Rate
Battery Discharging Rate
Battery Efficiencies
Power Consumption / Generation Chart
Analysis.3Panels.PanelList
Battery size
Building battery storage potential
Safety
Installation Costs,
Installation Procedures / Wiring
Maintenance
Battery Lifetime Costs
Battery Lifetime Environmental Impact
Battery Monitor Capability
Contact Battery Vendors
Find potential batteries on-line
Is there an available expertise resource?
Contact Installation Contractors
Where can we get help / resources from to create these renderings?
What Building Perspectives are Required?
Look on the building
Fit within the neighboring buildings
Adjust Calc. # of Panels on Building & Their Location to meet Code
Analysis.3Panels.PanelList
What expertise and other resources are available to answer these questions / develop this criteria?
Returning back to the main deliverable there are still a couple deliverables to expand on…
Analysis.BattStorage&BldgRenders

## Slide 25
Solar Panel Analysis for Community Hall
Analysis.
Battery Storage Options
Building Renderings with Solar Panels Installed for min 1 Top Panel Choice
Electricity Costs
“Excess” Energy
Generation
Battery Storage Capacity
Battery Charging Rate
Battery Discharging Rate
Battery Efficiencies
Power Consumption / Generation Chart
Analysis.3Panels.PanelList
Battery size
Building battery storage potential
Safety
Installation Costs,
Installation Procedures / Wiring
Maintenance
Battery Lifetime Costs
Battery Lifetime Environmental Impact
Battery Monitor Capability
Contact Battery Vendors
Find potential batteries on-line
Is there an available expertise resource?
Contact Installation Contractors
Where can we get help / resources from to create these renderings?
What Building Perspectives are Required?
Look on the building
Fit within the neighboring buildings
Adjust Calc. # of Panels on Building & Their Location to meet Code
Analysis.3Panels.PanelList
What expertise and other resources are available to answer these questions / develop this criteria?
Notice the reference to part of a previously developed branch
Notice the reference to part of a previously developed branch
Analysis.BattStorage&BldgRenders

## Slide 26
Solar Panel Analysis for Community Hall
Analysis.
Battery Storage Options
Building Renderings with Solar Panels Installed for min 1 Top Panel Choice
Electricity Costs
“Excess” Energy
Generation
Battery Storage Capacity
Battery Charging Rate
Battery Discharging Rate
Battery Efficiencies
Power Consumption / Generation Chart
Analysis.3Panels.PanelList
Battery size
Building battery storage potential
Safety
Installation Costs,
Installation Procedures / Wiring
Maintenance
Battery Lifetime Costs
Battery Lifetime Environmental Impact
Battery Monitor Capability
Contact Battery Vendors
Find potential batteries on-line
Is there an available expertise resource?
Contact Installation Contractors
Where can we get help / resources from to create these renderings?
What Building Perspectives are Required?
Look on the building
Fit within the neighboring buildings
Adjust Calc. # of Panels on Building & Their Location to meet Code
Analysis.3Panels.PanelList
What expertise and other resources are available to answer these questions / develop this criteria?
Analysis.BattStorage&BldgRenders
There seems to be a lot of work and a lot of unknowns for these deliverables. Since they’re not as central of a priority for your stakeholder, you can work out an agreement with your stakeholder to cut these from the
Notice the dashed line to show these were cut from the scope. Don’t throw this away as it may be a good place to start for your next phase.
project scope for this phase of the work.

## Slide 27
And now, you’re done! Well at least well enough to get started with the next steps of your work, and assigning tasks among team members. Now is a great time to translate all of your slides into a timeline. You may likely find a few more tasks / deliverables, performance criteria, needed data and questions in doing so as you review your work here.
Check out the Timeline Guide on how to create a timeline. There is some overlap in the themes and steps in the timeline guide with what is discussed in this guide, and so you may be able to replace some timeline Steps (such as determining subtasks) with the work that you have already done here.
You could also translate your question tree here to a PERT Chart or you can combine your question tree into one large complete one and possibly color code it as well. Either way, make sure you also read Defining Deliverables and all of its Tips section so you’ll create your own question tree as effectively as possible.