## Chassis Design
Cornell Cup USA presented by Intel
Sample Interface Trace Matrix Excerpt : Chassis Design Subsystem Sheet
Chassis Design | Motor Drive | Power | True Budget Total | Value / Target Budget Total | Units | Estimate? | Last Updated | Last Updated By | Interface Champ. | Est. Update Due Date | Actual Due Date | Row # | Chassis Design
| Provided to | Provided to |  | 144 | in3 | X | 2012-06-25 | Jin | Nero | 2012-07-15 | 2012-08-01 | 5 | Total Volume Max
| Provided to |  |  | 10 | in3 | X | 2012-06-26 | Jin | Nero | 2012-07-15 | 2012-08-01 | 6 |  | Total Volume Allocated to Motors
|  | Provided to |  | 12 | in3 | X | 2012-06-26 | Jin | Nero | 2012-07-15 | 2012-08-01 | 7 |  | Total Volume Allocated to Power subsystem
| Received From |  |  | 7.9481 | in3 |  | 2012-07-11 | Horitz | Nick | 0 | 2012-07-11 | 8 |  | Actual Volume used by Motors
|  | Received From |  | 12.5 | in3 |  | 2012-07-20 | Susan | Heidi | 0 | 2012-07-20 | 9 |  | Actual Volume used by Power subsystem
| Provided to |  | 2.294 | 2.5 | kg | X | 2012-06-28 | Hilary | Octavier | 2012-07-15 | 2012-08-01 | 10 | Total Component Weight Max
| Provided to |  |  | 2 | kg | X | 2012-06-29 | Hilary | Octavier | 2012-07-15 | 2012-08-01 | 11 |  | Total Weight Allocated to Motors
|  | Provided to |  | 0.5 | kg | X | 2012-06-29 | Hilary | Octavier | 2012-07-15 | 2012-08-01 | 12 |  | Total Weight Allocated to Power subsystem
| Provided to |  |  | 2.084 | kg |  | 2012-07-11 | Horitz | Nick | 0 | 2012-07-11 | 13 |  | Actual Weight used by Motor drive subsystem
|  | Provided to |  | 0.21 | kg | X | 2012-07-20 | Susan | Heidi | 0 | 2012-07-20 | 14 |  | Actual Weight used by Power subsystem
| Received From |  |  | MotorGuide (Sec 1.2) | .docx |  | 2012-07-29 | Justin | Justine | 0 | 2012-08-15 | 15 | Motor Installation Guide
|  | Received From |  | PowerBoardInstructions (Sec 2.1) | .docx |  | 2012-07-16 | Susan | Heidi | 0 | 2012-08-15 | 16 | Power Board Connection Instructions
|  |  | 1244 | 1500 | $ |  | 2012-06-15 | Xing | Lesslie | 2012-06-15 | 2012-07-15 | 17 | Total Cost Allowed
|  |  |  | 150 | $ |  | 2012-07-13 | Xing | Lesslie |  | 2012-07-15 | 18 |  | Chassis Design Cost
| Received From |  |  | 864 | $ |  | 2012-07-19 | Kelsey | Marc | 2012-07-05 | 2012-07-18 | 19 |  | Motor Cost
|  | Received From |  | incl. components & shipping: 230 | $ |  | 2012-07-22 | Susan | Heidi | 2012-07-15 | 2012-07-20 | 20 |  | Power Board Cost

## Motor Drive
Cornell Cup USA presented by Intel
Sample Interface Trace Matrix Excerpt : Motor Drive Subsystem Sheet
Chassis Design | Motor Drive | Power | True Budget Total | Value / Target Budget Total | Units | Estimate? | Last Updated | Last Updated By | Interface Champ. | Est. Update Due Date | Actual Due Date | Row # | Motor Drive Subsystem
[12 empty] | 5 | Power Information
|  | Provided to |  | 24 | V |  | 2012-07-11 | Yashoda | Jose |  | 2012-07-12 | 6 |  | Motor Voltage
|  | Provided to |  | 1.7 | A |  | 2012-07-11 | Yashoda | Jose |  | 2012-07-12 | 7 |  | Motor Current
|  | Provided to |  | 30 | W |  | 2012-07-11 | Yashoda | Jose |  | 2012-07-12 | 8 |  | Motor power rating
|  | Received From |  | less than 6 | A | X | 2012-07-12 | Archie | Fritz | 2012-07-01 | 2012-07-12 | 9 |  | Max Current Draw
|  | Received From |  | 24 | V |  | 2012-07-12 | Archie | Fritz | 2012-07-01 | 2012-07-12 | 10 |  | Max Voltage Supplied
|  | Provided to |  | 24 | min. | X | 2012-06-28 | Allison | Yulia | 2012-06-30 | 2012-07-15 | 11 | Maximum Duration Usage
Provided to |  |  |  | 216 | $ |  | 2012-07-19 | Kelsey | Marc | 2012-07-05 | 2012-07-18 | 12 | Motor Cost
[12 empty] | 13 | Motor Dimensions
Provided to |  |  |  | 62.5 | mm |  | 2012-07-11 | Horitz | Nick | 2012-07-05 | 2012-07-11 | 14 |  | Motor Length
Provided to |  |  |  | 50 | mm |  | 2012-07-11 | Horitz | Nick | 2012-07-05 | 2012-07-11 | 15 |  | Motor Dia.
Received From |  |  |  | 10 | in3 | X | 2012-06-26 | Jin | Nero | 2012-07-15 | 2012-08-01 | 16 |  | Total Volume Allocated to Motors
Provided to |  |  |  | 7.9481 | in3 |  | 2012-07-11 | Horitz | Nick |  | 2012-07-11 | 17 |  | Actual Volume used by Motors
[12 empty] | 18 | Motor Weight
Received From |  |  |  | 2 | kg | X | 2012-06-29 | Hilary | Octavier | 2012-07-15 | 2012-08-01 | 19 |  | Total Weight Allocated to Motors
Provided to |  |  |  | 521 | g |  | 2012-07-11 | Horitz | Nick | 2012-07-05 | 2012-07-11 | 20 |  | Motors Weight
Provided to |  |  |  | 2.084 | kg |  | 2012-07-11 | Horitz | Nick |  | 2012-07-11 | 21 |  | Actual Weight used by Motor drive subsystem
Provided to |  |  |  | MotorGuide (Sec 1.2) | .docx |  | 2012-07-29 | Justin | Justine |  | 2012-08-15 | 22 | Motor Installation Guide

## Power
Cornell Cup USA presented by Intel
Sample Interface Trace Matrix Excerpt : Power Subsystem Sheet
Chassis Design | Motor Drive | Power | True Budget Total | Value / Target Budget Total | Units | Estimate? | Last Updated | Last Updated By | Interface Champ. | Est. Update Due Date | Actual Due Date | Row # | Power Subsystem
| Provided to |  |  | 5, 12, 24 | V |  | 2012-07-12 | Archie | Fritz | 2012-07-01 | 2012-07-12 | 5 | Voltages Supplied
| Received From |  |  | 24 | V |  | 2012-07-11 | Yashoda | Jose | 0 | 2012-07-12 | 6 | Motor Voltage
| Received From |  |  | 1.7 | A |  | 2012-07-11 | Yashoda | Jose | 0 | 2012-07-12 | 7 | Motor Current
| Received From |  |  | 30 | W |  | 2012-07-11 | Yashoda | Jose | 0 | 2012-07-12 | 8 | Motor power rating
| Provided to |  |  | less than 6 | A | X | 2012-07-12 | Archie | Fritz | 2012-07-01 | 2012-07-12 | 9 | Max Current Draw
| Provided to |  |  | 24 | V |  | 2012-07-12 | Archie | Fritz | 2012-07-01 | 2012-07-12 | 10 | Max Voltage Supplied
| Received From |  |  | 24 | min. | X | 2012-06-28 | Allison | Yulia | 2012-06-30 | 2012-07-15 | 11 | Maximum Duration Usage
Provided to |  |  |  | incl. components & shipping: 230 | $ |  | 2012-07-22 | Susan | Heidi | 2012-07-15 | 2012-07-20 | 12 | Power Board Cost
Provided to |  |  |  | PowerBoardInstructions (Sec 2.1) | .docx |  | 2012-07-22 | Rebecca | Ahmed |  | 2012-08-15 | 13 | Power Board Connection Instructions
Provided to |  |  |  | 12 x 2.5 x 1 | in. |  | 2012-07-16 | Susan | Heidi |  | 2012-08-15 | 14 | Power Board Dimensions
Received From |  |  |  | 12 | in3 | X | 2012-06-26 | Jin | Nero | 2012-07-15 | 2012-08-01 | 15 | Total Volume Allocated to Power subsystem
Provided to |  |  |  | 12.5 | in3 |  | 2012-07-20 | Susan | Heidi |  | 2012-07-20 | 16 | Actual Volume used by Power subsystem
Received From |  |  |  | 0.5 | kg | X | 2012-06-29 | Hilary | Octavier | 2012-07-15 | 2012-08-01 | 17 | Total Weight Allocated to Power subsystem
Provided to |  |  |  | 0.21 | kg | X | 2012-07-20 | Susan | Heidi |  | 2012-07-20 | 18 | Actual Weight used by Power subsystem